## Sheet1
PRJ566
PRJ566 Weekly Deliverables | Team Self Selection & Project Selection | Proposal Preparation (3%) | Project Overview (4%) | Requirements Elicitation: Functional & non-functional (8%) | Process & Data Modelling (30%) Midterm Test (25%) Total (55%) | [5 empty] | Database Design (5%) | Implementation Planning (10%) |  | Final Submission (15%)
| Week 1 | Week 2 (3%) | Week 3 (4%) | Week 4 (8%) | Week 5 (8%) | Week 6 (3%) | Week 7 (10%) | Break | Week 8 (2%) | Week 9 (7%) | Week 10 (5%) | Week 11 (5%) | Week 12 (5%) | Week 13 (5%) | Week 14 (10%)
Artifacts | 1- Creating your self-organizing Teams 2- Draft Business Proposal. | 1- Business Case Proposal. (Final) | Software Requirements Specification (SRS Template - Pages 1 to 6.): Section 1 (1.1 to 1.6) Section 2 (2.1 only) (4%) | 1- Stakeholders' List. (1%) 2- Functional Requirements. (3%) 3- Nonfunctional Requirements (1%) 4- Project Scope. (2%) | 1- System Risks (1%) 2- Operating Environment (1%) 3- Prototype First Attempt: UI/UXD - Wireframes/Mock-ups (5%) | 1- Data Flow Diagrams (DFDs.) (1%) 2- Activity Diagram. (1%) | Use Case Specifications with corresponding interface mockups including: 1- Business Rules. (1%) 2- System Use Case Diagrams. (2%) 3- Use Case Descriptions. (6%) | Break Week | 1- Finalized System Mockups (Prototype) (1%) 2- PPT and Video Development (1%) | 1- Domain Class Diagram (2%) 2- Team Prototype Presentations (4%) | 1- RDBMS: ERD, Data Dictionary (4%) OR 1- NoSQL (4%) | 1- Work Breakdown Structure (WBS.) (2%) 2- Project Milestones & Acceptance Criteria. (2%) | 1- Waterfall Implementation Schedule using MS Project tool (.mpp) (4%) OR Hybrid Agile Product Backlog (Sprints & User Stories) (4%) | 1- Develop the final Video presentation (2.5%) 2- Completed SRS (2.5%) | 1- Teams Presentation Day (whole class in attendance)
Project Management & Reporting |  |  | GitHub Setup (0%) | GitHub Updates: Tasks and Progress Report Walkthrough (1%) | GitHub Updates: Tasks and Progress Report Walkthrough (1%) | GitHub Updates: Tasks and Progress Report Walkthrough (1%) | GitHub Updates: Tasks and Progress Report Walkthrough (1%) |  | Test 25% | GitHub Updates: Tasks and Progress Report Walkthrough (1%) | GitHub Updates: Tasks and Progress Report Walkthrough (1%) | GitHub Updates: Tasks and Progress Report Walkthrough (1%) | GitHub Updates: Tasks and Progress Report Walkthrough (1%)
Due dates | 2022-09-11 | 2022-09-18 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 2022-10-16 | 2022-10-30 |  | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-10-11 | In-class Presentation
All artifacts (team & individual) are to be uploaded to MS teams and are due on Sunday @11:59 PM Except for week 14. Week 14 delverable is due on the presentation day. All artifacts after revision must be included in the SRS. Project schedule in MS Project. Please note that if your team missed the due date you will get a Zero unless you have approval from your professor prior to the due date